## Title Page
BUDGET
Dev Team: | Team Greg
Project Title: | Breaking Greg: A Man's World
Start Date: | 2022-02-11
End Date: | 2022-09-12
Total Budget AUD$ | 60000
Actual Cost AUD$ | 51835.6

## Team Timesheet
Team Timesheet
Week 1
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS | Rates | Weekly Total
Programmer 1 (Luke Stanbridge) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Programmer 2 (Blake Page) |  |  | 0 | 0 | 0 |  |  | 0 | 32.79 | 0
Lead Artist (Heather Barnett) |  |  | 8 | 8 | 8 |  |  | 24 | 31.88 | 765.12
Artist 1 (Flynn Eickhoff) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 2 (Luckas Mack) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 3 (Jasmine Wang) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) |  |  | 8 | 8 | 8 |  |  | 24 | 51.92 | 1246.08
Lead Designer (Jackson Hole |  |  | 8 | 8 | 8 |  |  | 24 | 36.62 | 878.88
Designer (Jared Threadgold) |  |  | 8 | 8 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 0 | 0 | 64 | 64 | 64 | 0 | 0 | 192 |  | 6349.2
Team Timesheet
Week 2
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS
Programmer 1 (Luke Stanbridge) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Programmer 2 (Blake Page) |  |  | 0 | 0 | 0 |  |  | 0 | 32.79 | 0
Lead Artist (Heather Barnett) |  |  | 8 | 8 | 8 |  |  | 24 | 31.88 | 765.12
Artist 1 (Flynn Eickhoff) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 2 (Luckas Mack) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 3 (Jasmine Wang) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) |  |  | 8 | 8 | 8 |  |  | 24 | 51.92 | 1246.08
Lead Designer (Jackson Hole |  |  | 8 | 8 | 8 |  |  | 24 | 36.62 | 878.88
Designer (Jared Threadgold) |  |  | 8 | 8 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 0 | 0 | 64 | 64 | 64 | 0 | 0 | 192 |  | 6349.2
Team Timesheet
Week 3
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS
Programmer 1 (Luke Stanbridge) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Programmer 2 (Blake Page) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Lead Artist (Heather Barnett) |  |  | 8 | 8 | 8 |  |  | 24 | 31.88 | 765.12
Artist 1 (Flynn Eickhoff) |  |  | 0 | 8 | 0 |  |  | 8 | 27.33 | 218.64
Artist 2 (Luckas Mack) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 3 (Jasmine Wang) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) |  |  | 8 | 8 | 0 |  |  | 16 | 51.92 | 830.72
Lead Designer (Jackson Hole |  |  | 8 | 8 | 8 |  |  | 24 | 36.62 | 878.88
Designer (Jared Threadgold) |  |  | 8 | 8 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 0 | 0 | 64 | 72 | 56 | 0 | 0 | 192 |  | 6283.52
Team Timesheet
Week 4
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS
Programmer 1 (Luke Stanbridge) |  |  | 8 | 0 | 8 |  |  | 16 | 32.79 | 524.64
Programmer 2 (Blake Page) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Lead Artist (Heather Barnett) |  |  | 8 | 8 | 8 |  |  | 24 | 31.88 | 765.12
Artist 1 (Flynn Eickhoff) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 2 (Luckas Mack) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 3 (Jasmine Wang) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) |  |  | 8 | 8 | 8 |  |  | 24 | 51.92 | 1246.08
Lead Designer (Jackson Hole |  |  | 8 | 8 | 8 |  |  | 24 | 36.62 | 878.88
Designer (Jared Threadgold) |  |  | 8 | 8 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 0 | 0 | 72 | 64 | 72 | 0 | 0 | 208 |  | 6873.84
Team Timesheet
Week 5
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS
Programmer 1 (Luke Stanbridge) |  |  | 4 | 8 | 8 |  |  | 20 | 32.79 | 655.8
Programmer 2 (Blake Page) |  | 6 | 4 | 8 | 8 |  |  | 26 | 32.79 | 852.54
Lead Artist (Heather Barnett) |  |  | 0 | 8 | 8 |  |  | 16 | 31.88 | 510.08
Artist 1 (Flynn Eickhoff) |  | 6 | 9 | 8 | 8 |  |  | 31 | 27.33 | 847.23
Artist 2 (Luckas Mack) |  |  | 0 | 8 | 8 |  |  | 16 | 27.33 | 437.28
Artist 3 (Jasmine Wang) |  |  | 9 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) | 6 | 6 | 12 | 8 | 8 | 3 | 2 | 45 | 51.92 | 2336.4
Lead Designer (Jackson Hole | 6 | 6 | 10 | 8 | 8 | 3 | 3 | 44 | 36.62 | 1611.28
Designer (Jared Threadgold) |  |  | 8 | 8 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 12 | 24 | 56 | 72 | 72 | 6 | 5 | 246 |  | 8610.93
Team Timesheet
Week 6
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS
Programmer 1 (Luke Stanbridge) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Programmer 2 (Blake Page) |  | 6 | 8 | 8 | 8 |  |  | 30 | 32.79 | 983.7
Lead Artist (Heather Barnett) |  |  | 8 | 8 | 8 |  |  | 24 | 31.88 | 765.12
Artist 1 (Flynn Eickhoff) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 2 (Luckas Mack) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 3 (Jasmine Wang) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) | 6 | 6 | 10 | 12 | 8 | 3 | 3 | 48 | 51.92 | 2492.16
Lead Designer (Jackson Hole | 6 | 6 | 10 | 12 | 8 |  |  | 42 | 36.62 | 1538.04
Designer (Jared Threadgold) |  |  | 8 | 8 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 12 | 18 | 76 | 80 | 72 | 3 | 3 | 264 |  | 9238.14
Team Timesheet
Week 7 (Polish week)
Development Team | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | TOTAL HOURS
Programmer 1 (Luke Stanbridge) |  |  | 8 | 8 | 8 |  |  | 24 | 32.79 | 786.96
Programmer 2 (Blake Page) |  | 2 | 8 | 11 | 8 |  |  | 29 | 32.79 | 950.91
Lead Artist (Heather Barnett) |  |  | 8 | 8 | 8 |  |  | 24 | 31.88 | 765.12
Artist 1 (Flynn Eickhoff) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 2 (Luckas Mack) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Artist 3 (Jasmine Wang) |  |  | 8 | 8 | 8 |  |  | 24 | 27.33 | 655.92
Management Team | [9 empty] | 0
Producer (Euan Wynne-Jones) | 4 | 6 | 10 | 12 | 8 |  |  | 40 | 51.92 | 2076.8
Lead Designer (Jackson Hole |  | 2 | 8 | 6 | 8 |  |  | 24 | 36.62 | 878.88
Designer (Jared Threadgold) |  |  | 8 | 12 | 8 |  |  | 24 | 29.35 | 704.4
TOTAL HOURS | 4 | 10 | 74 | 81 | 72 | 0 | 0 | 237 |  | 8130.83
51835.6

## Rates $
Development Team | Staff | $ Rate per hour
Programmer Standard | Luke S, Blake P | 32.79
Lead Artist | Heather B | 31.88
Artist | Jasmine W, Flynn E, Luckas M | 27.33
Lead Designer | Jackson H | 36.62
Designer | Jared T | 29.35
Management Team
Producer | Euan WJ | 51.92