## Fees
| Wage | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | TOTAL COST
Producer (Euan WJ) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Lead Designer (Jackson H) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Lead Programmer (Blake P) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Lead Artist (Heather B) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Designer/UI/ Sound (Jarad T) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Artist/ Vision Holder (Flynn E) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Artist 3D/UI/VFX (Jasmine W) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Artist/ Animation (Lukas M) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 6591.2
Programmer (Luke S) | 42.8 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 5649.6
AVERAGE WAGE | 42.8
DO NOT TOUCH |  | Week 7: Total Cost | 58379.2

## Schedule
EPIC | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | PROGRAMMING
Prototype PlayerCharacter movement | [8 empty] | ART | bar: 2022-10-17
Prototype Level prefab | 2022-10-17: 2 | DESIGN
Create Female Character Mesh | [8 empty] | ANIMATION | bar: 2022-10-17
Create Male Character Mesh | [8 empty] | AUDIO | bar: 2022-10-17
Rigging Character Model (s) (M/F) | 2022-10-17: 2; 2022-10-31: 1 | UI
Animating Player character (6 Anims) | 2022-10-24: 2; 2022-10-31: 2; 2022-11-07: 2; 2022-11-14: 2 | UX
Animating NPC charracters (4 Anims) | 2022-10-24: 2; 2022-10-31: 2; 2022-11-07: 2; 2022-11-14: 2 | DOCUMENTATION
Enviromental Props (L-P) | [8 empty] | ALL | bar: 2022-11-14 to 2022-11-21
Environmental Props (M-P) | bar: 2022-10-31 to 2022-11-07
Environmental Props (H-P) | bar: 2022-10-17 to 2022-10-24
Prefabs of Assets using Pipeline | bar: 2022-10-17 to 2022-12-05
Documentation (GDD, TDD, AB) | 2022-10-17: 3
Sound design & script managment | bar: 2022-10-31
VFX Creation(6 assets) | bar: 2022-11-14 to 2022-11-21
VFX implimentation | bar: 2022-11-21 to 2022-11-28
UI assets Creation | bar: 2022-10-31
UI Implimentation | bar: 2022-11-07
Menu Screens (L-P) | bar: 2022-11-28 to 2022-12-05
Medium Prority Animation (4) | bar: 2022-11-14 to 2022-11-21
Low Priority Animations (3) | bar: 2022-11-21 to 2022-11-28
Score Scripting | bar: 2022-10-24
Level creation scripting | bar: 2022-10-17
Ability scripting | bar: 2022-10-31 to 2022-11-14
Object/Prop Scripting | bar: 2022-10-24
Bug Fixing | bar: 2022-10-31 to 2022-12-05
TOTAL STAFF: | 12 | 8 | 11 | 9 | 9 | 5 | 4 | 2
WEEKLY COST: | 513.6 | 342.4 | 470.8 | 385.2 | 385.2 | 214 | 171.2 | 85.6
TOTAL COST: | 2022-10-17: 2568
AVERAGE WAGE: | 2022-10-17: 42.8