## Sheet1
Risk Tracking - Project:
ID | Description of Risk | Impact | Risk Response | Risk Level | Risk Owner | Notes
1 | Room/ Level generation | Design Pivot maybe required | Changing game design to linear developed level | Medium | Blake | This is an ambicious system, however Blake is confident is can be created in a week
2 | Character/ NPC animations | Combat/ Movment feeling janky | Using placeholder anims untill final ones are ready | High | Lukas, Flynn | Animations take a long time to create, this doesn’t account for the rigging process which is required to get this started
3 | Performance will many discuctable assets | Game runs badly on less powerful machines | Developing Poly limits for assets | Medium | Flynn, Designers | Having a deconstructed version of many assets takes time, and will raise poly limits
4 | Not getting the feeling of the game right | Game is not engadging enough | Giving adequate time for refinment | Low | Jarad, Euan, Jackson | Sound design plays heavily into game feelings
5 | Difficulty balancing & Scaling | experince is unfair & not fun | Giving adequate time for refinment | Low | Jarad, Euan, Jackson | Getting artists to playtest in polish phase if all assets needed are created
6 | Source control issues | loosing work of teammembers | teaching lead artist to use only | low | Euan, Flynn, Heather | Having less people pushing to source control minimizes the risks of things going wrong.
7 | Consistanty of art assets | Game has a lack of cohesion | Having assets needing to be reviewed prior to implimentation | Medium | Euan, Flynn, Heather, Jasmine | Having a collective vision for the art style is important between characters & environment
8 | Software crashes | loss of files | Source tree & backups | Medium | Everyone | Unity & maya is prone to crashing
9 | Team productivity | Rate of Work drop off | Producer communication with team if this occurs | Medium | Euan, Rest of the Team | Slow days happen, but meeting deadlines is still essentail
10 | Hardware failure | loss of files | Backup work | Low | Everyone | Very unlikely but backup procedures are always good habits to be in
Risk Tracking - WHS
ID | Description of Hazard | Potential Risks | Action Required | Risk Level | Location | Notes
1 | Loose cables | Trip hazard | Procedure plan | Medium | Level 5 | Making sure cables are tied back and not in the way of feet
2 | Poor posture | Back pains | Active breaks, Good chairs | Medium | Level 5 | Having stretch breaks, making sure to sit peroperly
3 | Screen time | Eye strain | Looking after personal Health | High | Level 5 | Having regular breaks
4 | Crunch period / Overtime | Mental Health | Plan effectivly for Sprints | Medium | Level 5 | Not over scoping so we don’t need to crunch & do overtime
5 | Liquids near computers | Shocks | Procedure plan | Low | Level 5 | Lids on drinks
6 | Bags in walkways | Trip hazard | Procedure plan | Low | Level 5 | Move them to an appoperate spot
7 | Not drinking enough | Dehydration | Looking after personal Health | Low | Level 5 | Drink water at lunch
8 | Tragic accident of teammember | Death | Ensure work is backed up | Low | Outside | send sad emoji to perental guardian via teams
9 | Excessive weight gain | Heart disease | fitness reaigeme | Low | KFC | Making good dietary choices, is an important part of mental health
10 | Starvation due to elevator malfunction | Low Team moral | Backup work | low | Elevator | Hopfully this doesn’t happen, but we will be prepared in the event of catastrophic loss of life